## Project Info
S. No | Project Name | Project Type | Development Langauge | API Server Location | Repo Server Location | Login credentials
1 | Remit4Sure | Android | Java |  | https://codendi.daemon.co.in/svnroot/AndroidEremit | Username: mahen.wcb1@gmail.com Password: Password@123
2 | e-Remit | iOS | Objective C | NA | https://codendi.daemon.co.in/svnroot/IOSEremit
3 | TTP |  | Objective C | http://125.17.102.130:8080/Betting.svc | https://codendi.daemon.co.in/svnroot/IOSTTPS | Username : sujibala Password : Test@123
4 | EMCO - iOS |  | Swift | http://125.17.102.143:8080/mobileapi/webapi/ | https://codendi.daemon.co.in/svnroot/EMCOIOS | Username : 900001 Password : 900001
5 | Nabto - Experio | iOS | Swift | NA | https://codendi.daemon.co.in/svnroot/NabtoExperio
6 | Nabto - Turbidity | iOS | Swift | NA | https://codendi.daemon.co.in/svnroot/NabtoTurbidity
7 | Nabto - PH | iOS | Swift | NA | https://codendi.daemon.co.in/svnroot/NabtoPH
8 | Nabto - TDS | iOS | Swift | NA | https://codendi.daemon.co.in/svnroot/NabtoTDS
9 | Xperio - Socket Application | iOS | Objective C | NA | https://codendi.daemon.co.in/svnroot/NabtoExperioSocket
10 | EMCO - Android | Android | Java | http://125.17.102.143:8080/mobileapi/webapi/ | https://codendi.daemon.co.in/svnroot/AndroidEMCO | Username : 900001 Password : 900001
11 | Nabto - Android | Android | Java | NA

## Tasks
S. No | Task | Description | Start Date | End Date | Status
1 | Daily team meeting | Review on daily action items
Review on all outstanding bugs and fixes
Review on blocked issues and their dependencies
Open discussion on enhancements and changes
2 | SRS/BRD document | Sharing a copy of SRS/BRD document with the team and making them understand the requirments for test cases preparation
3 | Reporting | Collect the reports from the team members on daily basis and share them as a consolidated to all stake holders on weekly/monthly basis
Represent the Mobility team in any status meeting
4 | UAT Support | Gather the acceptance criteria from UAT users to understand the parameters for their evaluation
Share the acceptance criteria with the team and work with them on collecting or creating UAT test cases
If necessary, train the UAT users on the application
If necessary, be on standby for any assistance during UAT
If necessary, perform some tasks during UAT and present the results to the client or UAT users for their go/no-go decision

## TTP
S. No | Module | Start Date | End Date | Status
1 | User Module * Login * Registration * Betfair Registration - After Signup (Redirected to Betfair website) *Forgot Password *Change Password *Home Page :- Show After Login/Registration. *ProfileView *Help (Static HTML pages) *Account Managment (Manage Profile/Change Password) | 2018-08-04 | 2018-08-04 | Completed
2 | Syndicate Game *Create New Game *Game Rules *League Standings *Place a Bet *Search Game *Invite Users * Join Game *Betting Transcation History *News Feed *Chat | 2018-08-04 | 2018-08-04 | Completed
3 | Single Game *Create New Game *Game Rules *Place a Bet *Betting Transcation History *News Feed | 2018-08-04 | 2018-08-04 | Completed

## EMCO
S. No | Module | Start Date | End Date | Status
1 | EMCO Phase 1 - Reactive Module *Login - common *Signup - common *Forgot Password/Change Password *Home Screen - Common *Reactive Menu *Log Complaint *Receive Compliants *Receive Complaint Detail *View Compliants *Dashboard | 2018-07-04 | 2018-07-04 | Completed
2 | EMCO Phase 2 - PPM Module *PPM details - Screen 1 *PPM details - Screen 2 *Preventive Maintenance Detail Screen *PPM Checklist Screen *After PPM Screen *Material Required *Material Used *PPE Required *Risk Assessment *Equipment Tools *PPM Findings/PPM recommendation *Feedback Screen *Rate the Service | 2018-07-04 | 2018-07-04 | Completed
3 | EMCO Phase 3 - Supervisor Module *Inspection Module Menu - Screen 1 *Reactive Request Verification - Hard /Soft Services *Reactive Request Verification - Hard /Soft Services List *Reactive Request Verification - Hard/Soft Services Detail *PPM Request Verification - Hard /Soft Services *PPM Request Verification - Hard /Soft Services List *PPM Request Verification - Hard/Soft Services Detail *PPM Request Verification - Hard/Soft Services Checklist *Assigned Inspection - Hard /Soft Services *Assigned Inspection - Hard /Soft Services List *Assigned Inspection - Hard/Soft Services Detail *Assigned Inspection - Hard/Soft Services Checklist *Random Inspection - Hard /Soft Services *Random Inspection - Hard /Soft Services List *Random Inspection - Hard/Soft Services Detail *Random Inspection - Hard/Soft Services Checklist | 2018-07-04 | 2018-07-04 | Completed

## e-Remit
S. No | Module | Start Date | End Date | Status
1 | User Module *Login *Sign Up - Redirected to website *Landing Screen - Shows merchat trade/money gram exchage rates *Change Password *Update Profile *Update Email *Left Slide Menu *Right Slide Menu | 2018-07-04 | 2018-07-04 | Completed
2 | Transaction *View transcation list *Refund *Reprocess *Review Payment | 2018-07-04 | 2018-07-04 | Completed
3 | Recipients *View recipients *Add Recipient *Edit Recipien | 2018-07-04 | 2018-07-04 | Completed
4 | Send Money *Select Recipient *Send Money *Review Payment *Payment Method | 2018-07-04 | 2018-07-04 | Completed
5 | Today’s Rates *View MerchantTrade/Moneygram rates | 2018-07-04 | 2018-07-04 | Completed
6 | Notifications *View Notifications | 2018-07-04 | 2018-07-04 | Completed
7 | Notifications *View Notifications | 2018-07-04 | 2018-07-04 | Completed
8 | Help *About Us *Terms&Conditions *Share *Support [Send Mail/call customer support] | 2018-07-04 | 2018-07-04 | Completed

## Nabto
S. No | Module | Start Date | End Date | Status
1 | Create Profile *Create Profile UI *Create key pair - Nabto API integration *GetFingerprint - Nabto API Integration *Save Profile - ProfileTools method *Open session for Profile - Nabto API integration | 2018-07-04 | 2018-07-04 | Completed
2 | OverView *OverView UI *Nabto startup - API integration *Open session for Profile - Nabto API integration *Get Devices Info - Nabto API integration *Handle undiscoverable/unreachable devices *Handle device selection *Handle Paired *Handle Unpaired *Handle Closed *Handle Offline | 2018-07-04 | 2018-07-04 | Completed
3 | Discovery *Discovery UI *Search & display discovered devices list *Discover- Nabto API integration *Handle device selection *Handle Paired *Handle Unpaired *Handle Closed *Handle Offline | 2018-07-04 | 2018-07-04 | Completed
4 | Pair *Pair UI *Pair with current user - Nabto API integration *Option to go to newly paired device | 2018-07-04 | 2018-07-04 | Completed
5 | Help *Help topics - UI & Implementation | 2018-07-04 | 2018-07-04 | Completed
6 | Devices *Light Control UI & Implmentation *Invoke RPC for getting device state *Invoke RPC for switching ON/Off state of light control | 2018-07-04 | 2018-07-04 | Completed
7 | Services ProfileTools *Save Profile [Username & Certificate] *Clear Profile [Username & Certificate] *Manage Username (Get/Set/Save) *Manage Certificate (Get/Set/Save) NabtoManager *Nabto startup *Nabto startupAndOpenGuestSession *Nabto openSessionForProfile *Nabto nabtoRpcSetDefaultInterface *Nabto shutdown *Nabto openSessionForProfile *Nabto create key pair - nabtoCreateSelfSignedProfile *Nabto get finger print - nabtoGetFingerprint *NabtoDevice Discover devices *Get devices information *Invoke RPC for fetching device public information *Invoke RPC for fetching current user information *Fetch System Permission *Fetch Default User Permission *Set security Details *EnableRemote Access *Enable Open For Pairing *Enable Grant Guest Remote Access Settings *Invoke RPC for setting device info *Invoke RPC for fetching system security info *Invoke RPC for setting system security info *Invoke RPC for reading system security info Device - User Management *Invoke RPC for fetching user info - *Invoke RPC for setting user info *Invoke RPC to set username *Invoke RPC to remove username | 2018-07-04 | 2018-07-04 | Completed

## Proposal done so far
URL | Username | Password | Folder
http://192.168.1.115:36320 | swapna.raj | daemon@123 | Mobility/Proposals
| S.No | Proposal Name | Proposal stored location | Folder
| 1 | App drive singapore | sharepoint | Mobility/Proposals
| 2 | Appointment Schedule | sharepoint | Mobility/Proposals
| 3 | Cab driver app | sharepoint | Mobility/Proposals
| 4 | Chips betting app | sharepoint | Mobility/Proposals
| 5 | doctor-patient app | sharepoint | Mobility/Proposals
| 6 | Fleet Management | sharepoint | Mobility/Proposals
| 7 | Foodies App | sharepoint | Mobility/Proposals
| 8 | Laundry App | sharepoint | Mobility/Proposals
| 9 | Mauritous App | sharepoint | Mobility/Proposals
| 10 | Milkinfotech | sharepoint | Mobility/Proposals
| 11 | NIC QMS App | sharepoint | Mobility/Proposals
| 12 | Queue Management App | sharepoint | Mobility/Proposals
| 13 | Real Estate | sharepoint | Mobility/Proposals
| 14 | Scrumcious Fruit | sharepoint | Mobility/Proposals
| 15 | Sikap | sharepoint | Mobility/Proposals
| 16 | Spectranet | sharepoint | Mobility/Proposals
| 17 | Telecom App | sharepoint | Mobility/Proposals
| 18 | Truck App | sharepoint | Mobility/Proposals

## ISO Process
| URL | Username | Password | Document Location
| http://192.168.1.115:36320 | swapna.raj | daemon@123 | sharepoint
S. No | Task | Document Location | Start Date | End Date | Status
1 | TTP Business Requirement Document | ISO_Process_Documentation/Development_Process/TTP | 2018-08-04 | 2018-08-04 | Completed
2 | TTP Feasibility Study | ISO_Process_Documentation/Development_Process/TTP | 2018-08-04 | 2018-08-04 | Completed
3 | TTP Technical Specification document | ISO_Process_Documentation/Development_Process/TTP | 2018-08-04 | 2018-08-04 | Completed
4 | TTP Functional Spefication document | ISO_Process_Documentation/Development_Process/TTP | 2018-08-04 | 2018-08-04 | Completed
5 | TTP Project Plan | ISO_Process_Documentation/Development_Process/TTP | 2018-08-04 | 2018-08-04 | Completed
6 | TTP Work Break Down Schedule | ISO_Process_Documentation/Development_Process/TTP | 2018-08-04 | 2018-08-04 | Completed
7 | Project Change Request Form | ISO_Process_Documentation/Development_Process/TTP | 2018-08-04 | 2018-08-04 | Completed

## Mobile SharePoint
| URL | Username | Password
| http://192.168.1.115:36320 | swapna.raj | daemon@123
S No | Documents Uploaded | Status | document location
1 | TTP BRD | Completed | ISO_Process_Documentation/Development_Process/TTP
2 | TTP Functional specification | Completed | ISO_Process_Documentation/Development_Process/TTP
3 | TTP user manual - PHASE 1 | Completed | ISO_Process_Documentation/Development_Process/TTP
4 | EMCO Scope - Phase 1 | In Progress
5 | EMCO phase 1 -user manual | In Progress
6 | EMCO Scope - Phase 2 | In Progress
7 | EMCO Scope - Phase 3 | In Progress